## Parity Checklist
ID | Title | Service crate | Kernel IPC | Shell plugin | Legacy handler(s) | Gap | Size | Est wk | Priority | Phase | Status | Owner | Dependencies | Acceptance | Notes
WI-01 | Port AI chat panel to shell (streaming + sessions) | nexus-ai | com.nexus.ai::config, stream_chat, stream_ask, session_load, session_save, session_list, session_delete | shell/src/plugins/nexus/ai/ (currently skeleton) | ai_config, ai_stream_chat, ai_stream_ask, ai_session_load, ai_session_save, ai_session_list, ai_session_delete | only-app | L | 2 | P0 | P2a | todo |  | WI-06 (event bridge subscription) | User can open AI chat, send a message, see streaming tokens render in real time; RAG 'Ask' against current forge returns cited sources; sessions persist across app restarts and are listable/deletable from the UI. | Kernel IPC + event forwarders already work for legacy. Port ChatPanel.tsx and AgentHistoryPanel.tsx equivalents; subscribe to com.nexus.ai.stream_start/chunk/done via kernel_subscribe.
WI-02 | Re-wire theme engine (brand-neutral redesign) | nexus-theme | com.nexus.theme::get_available_themes, apply_theme, compute_variables, get_available_snippets, toggle_snippet, reorder_snippets, get_theme_config, set_mode | shell/src/plugins/core/themeService/ (intentionally excluded per main.tsx comment) | get_available_themes, apply_theme, compute_variables, get_available_snippets, toggle_snippet, reorder_snippets, get_theme_config, set_mode | only-app | L | 2 | P1 | P2a | todo |  |  | Shell loads with default theme (dark), user can switch light/dark/system from settings; snippet cascade works; plugin-driven theme changes propagate via kernel bus and update :root CSS variables; no hardcoded 'Forge Ember' / 'Forge Paper' product names remain. | Template's themeService plugin deliberately not loaded (comment in shell/src/main.tsx). Redesign manifest names to be brand-neutral; port snippet UI from app/src/components/settings/tabs/.
WI-03 | Finish editor transaction wiring (Phases 0-8) | nexus-editor | com.nexus.editor::open, close, get_tree, save, apply_transaction, undo, redo, list_open, sync_content | shell/src/plugins/nexus/editor/ | editor_apply_transaction, editor_undo, editor_redo | partial | L | 2 | P0 | P2a | todo |  |  | editor-transaction-wiring-plan.md Phases 0-8 all marked complete; CM6 integration functional; echo-suppression works; session lifecycle refcount verified; undo/redo delegated to kernel UndoTree (not CM history); dirty-state revision-based. | Per editor-transaction-wiring-plan. Current shell editor works for basics but full transaction model may be incomplete. Validate against plan phases.
WI-04 | Keybinding overrides UI (HotkeysTab) | (shell-local, no kernel service) | (none — shell-side persistence via configStore) | shell/src/plugins/core/settings/ (new subview) | get_keybinding_overrides, set_keybinding_override, clear_keybinding_override | only-app | S | 0.5 | P1 | P2a | todo |  |  | Settings > Keybindings tab lists all registered commands with current bindings; user can rebind, clear, reset; overrides persist across restart; conflicts surface visibly. | KeybindingRegistry exists in shell; no persistence UI yet. Port HotkeysTab.tsx logic.
WI-05 | Saved terminal commands sidebar | nexus-terminal | com.nexus.terminal::saved_list, saved_create, saved_update, saved_delete, saved_reorder | shell/src/plugins/nexus/terminal/ (new sub-view) | term_saved_list, term_saved_create, term_saved_update, term_saved_delete, term_saved_reorder | only-app | S | 0.5 | P2 | P2a | todo |  |  | Terminal plugin exposes saved-commands side panel; user can add, edit, reorder, delete; click executes in active session; persists across restart. | Kernel IPC is ready; 5 handlers already implemented. Frontend-only port.
WI-06 | Generalize kernel_subscribe usage across streaming plugins | (none — shell bridge) | kernel_subscribe / kernel_unsubscribe (bridge.rs) | shell/src/host/PluginAPI.ts — api.kernel.on(topic, handler) | (N/A — legacy has bespoke per-topic forwarders) | partial | S | 0.5 | P0 | P2a | todo |  |  | Shell plugins can subscribe to any com.nexus.* topic prefix via api.kernel.on(topic, handler) and receive all matching events; cleanup on plugin deactivate proven to release subscriptions (no leak in ExtensionHost reload test). | Bridge commands exist. Validate end-to-end and document usage in @nexus/extension-api.
WI-07 | Agent panel: approval loop + streaming progress | nexus-agent | com.nexus.agent::plan, run, run_plan, execute_step, history_list, history_get, history_delete + events run_start, step_start, step_done, run_done | shell/src/plugins/nexus/agent/ | agent_plan, agent_run, agent_run_plan, agent_execute_step, agent_history_list, agent_history_get, agent_history_delete | partial | M | 1 | P1 | P2b | todo |  | WI-06 | User can submit goal, see plan rendered, step through with approval loop, view streaming step progress, browse/delete persisted history. | Plugin renders; some flows incomplete. Verify all 7 IPC commands exercised by UI.
WI-08 | Skills browser: render with params | nexus-skills | com.nexus.skills::list, get, render, reload | shell/src/plugins/nexus/skills/ | skills_list, skills_get, skills_render, skills_reload | partial | S | 0.5 | P2 | P2b | todo |  |  | User can browse skills, select one, fill parameter form, see rendered output; reload picks up on-disk changes. | Browser exists; render with parameter substitution may need porting from legacy SkillsPanel.tsx.
WI-09 | Workflow: list/get/reload/validate UI flow | nexus-workflow | com.nexus.workflow::list, get, reload, validate | shell/src/plugins/nexus/workflow/ | workflow_list, workflow_get, workflow_reload, workflow_validate | partial | S | 0.5 | P2 | P2b | todo |  |  | User can list workflows, view TOML, validate without loading, trigger reload; errors surface inline. | Browser exists; validate step may not be ported.
WI-10 | Bases: validate granular IPC (13 handlers) | nexus-storage (bases module) + nexus-database | com.nexus.storage::base_load, base_create, base_record_{create,update,delete,soft_delete,restore}, base_property_{create,update,delete,rename}, base_view_{create,update,delete} | shell/src/plugins/nexus/bases/ (Phases 1-6 claimed complete) | load_forge_base, save_forge_base, db_apply_view | partial | M | 1 | P2 | P2b | todo |  |  | Smoke-test each of 13 base_* handlers from shell plugin against a real .bases file; CRUD works for text/number/select/date/checkbox/formula/rollup columns; Table + Board + Calendar + Gallery + Timeline all render; CSV import/export round-trips. | Shell uses finer-grained IPC than legacy's single db_apply_view. Architecturally better; just needs validation pass.
WI-11 | Canvas: live-data validation + kernel IPC pass | nexus-storage (canvas module) | com.nexus.storage::canvas_read, canvas_write, canvas_patch, canvas_nodes, canvas_edges + com.nexus.linkpreview::fetch | shell/src/plugins/nexus/canvas/ (Phases 1-6 claimed complete) | (legacy has no canvas) | new-only | M | 1 | P2 | P2b | todo |  |  | Open a real .canvas file, edit with drag/select/create, save persists (atomic via canvas_patch), minimap + auto-layout work, export PNG/SVG/PDF succeeds, embedded markdown/image/terminal nodes render. | Primarily validation; implementation claims complete per canvas-shell-plan.md.
WI-12 | Terminal: upgrade from poll to streaming events | nexus-terminal | com.nexus.terminal::pump, read_output (current poll) → com.nexus.terminal.output.<session_id> (new stream event) | shell/src/plugins/nexus/terminal/ | term_pump, term_read_output | partial | M | 1 | P2 | P2b | todo |  | WI-06 | Terminal output streams via kernel event bus rather than 100ms polling; CPU usage drops to near-zero when idle; latency improves to <16ms typical. | Stretch: keep poll as fallback for very slow subscribers. Bonus item per integration review.
WI-13 | URI handler registry + dispatch_uri port | (shell-local registry) | (none — UI extension point) | shell/src/registry/UriHandlerRegistry.ts (new) | dispatch_uri, list_plugin_uri_handlers | only-app | S | 0.5 | P2 | P2c | todo |  |  | Plugins can register URI handlers via api; nexus://... links from outside the app route to correct plugin handler; deep-link flows (open specific note by URI) work. | Ship before v1 only if users have nexus:// links saved. Defer otherwise.
WI-14 | Persistence migration script (legacy → shell-state.json) | (standalone tool) | (none) | scripts/migrate-shell-state.ts (new) | get_layout_persistence, save_layout_persistence | architectural-diff | S | 0.5 | P1 | P2c | todo |  |  | Run script on a legacy install → produces shell-state.json + workspace.json in new shell's expected locations; existing tabs, split sizes, last-forge-path preserved. | Schemas differ (LayoutNode vs. ShellState+Leaf). Users on legacy should have smooth first-launch in new shell.
WI-15 | DECISION: Layout presets — keep as named Leaf snapshots? | (shell-local if kept) | (none) | shell/src/workspace/PresetManager.ts (if decided) | get_default_layout, get_layout_preset, list_layout_presets | architectural-diff | M | 1 | P3 | P2c | todo |  |  | Decide: retain preset concept (Obsidian/Vibe/Dev) or drop it. If retained, implement as named Leaf tree snapshots; if dropped, document rationale in ADR. | Preset-picker was a PRD-07 feature. Low user count? Drop. If retained, implement.
WI-16 | DECISION: Menu bar — reintroduce or palette-only? | (shell-local if kept) | (none) | shell/src/plugins/nexus/menuBar/ (if decided) | list_plugin_menu_items | architectural-diff | M | 1 | P3 | P2c | todo |  |  | Decide: retain native MenuBar (File/Edit/View...) as a plugin, or commit fully to palette-first UX. Document the decision in an ADR. | Palette covers most cases. MenuBar is useful for discoverability on macOS especially.
WI-17 | DECISION: Ribbon vs activity bar contribution API alignment | (shell-local) | (none) | shell/src/plugins/nexus/activityBar/ | list_plugin_ribbon_items | architectural-diff | XS | 0.25 | P3 | P2c | todo |  |  | activityBar contribution API is documented in @nexus/extension-api with same expressiveness as legacy ribbon (icon, tooltip, badge, ordering, onClick). Migration note in docs. | Mostly naming / API polish. Low effort.
WI-18 | Plugin capability listing surfaced in shell settings | nexus-plugins | (shell introspection — list declared capabilities per plugin) | shell/src/plugins/nexus/pluginsMgmt/ | list_plugin_capabilities | only-app | S | 0.5 | P1 | P2c | todo |  |  | Settings > Plugins tab shows each plugin's declared capabilities with risk-level labels; prepares for install-time prompt in Phase 3. | Precursor to install-time capability prompt (MK F-5.1.1, Phase 3).
WI-19 | Activation events (deferred plugin load) | nexus-plugins | (plugin loader) | shell/src/host/ExtensionHost.ts | list_plugin_activations | only-app | M | 1 | P2 | P2c | todo |  |  | Shell plugins can declare activation events (onView, onCommand, onUri, onLanguage, etc.); ExtensionHost defers load until event fires; cold-boot time improves measurably. | Fixes O(n) cold-start scaling per FORGE-UI-PLAN deferred item.
WI-20 | @nexus/extension-api: regenerate types via ts-rs + wire | nexus-plugin-api (source) → packages/nexus-extension-api (target) | (type definitions) | all shell plugins switch imports | (N/A — package currently unused) | new-only | M | 1 | P0 | P2a | todo |  |  | Capability, NexusEvent, IpcError, PluginInfo, TrustLevel et al. are generated from nexus-plugin-api via ts-rs; every shell plugin imports from @nexus/extension-api (zero raw Tauri/kernel imports); guardrail test enforces this. | Package is already scaffolded at packages/nexus-extension-api/ v1.0.0 but zero importers. Wire it.
WI-21 | File tree parity: legacy features (context menu, drag-drop) | nexus-storage | com.nexus.storage::list_dir, create_file, create_dir, rename_entry, delete_entry | shell/src/plugins/nexus/files/ | create_forge_file, create_forge_dir, rename_forge_entry, delete_forge_entry | partial | S | 0.5 | P1 | P2a | todo |  |  | Right-click on file/folder shows legacy-equivalent menu (new file/folder, rename, delete, reveal, copy path); drag-to-move works; keyboard shortcuts (F2 rename, Del delete) bound. | Shell files plugin is live but polish gap vs. legacy FileTree.tsx. Small targeted work.
WI-22 | Validation guardrail: prevent new #[tauri::command] in nexus-app | (workspace-level test) | (none) | crates/nexus-bootstrap/tests/dep_invariants.rs (extend existing test) | (meta — enforces the freeze policy) | new-only | XS | 0.25 | P0 | P2a | todo |  |  | Build fails if any new line containing `#[tauri::command]` is added to crates/nexus-app/src/ beyond the current baseline count (95). Test message points the author to CONTRIBUTING.md. | Structural enforcement of the freeze; prevents agent or human regressions. Simple grep-style assertion in the existing dep_invariants test.
WI-23 | Validation guardrail: shell plugins don't import raw Tauri APIs | (shell-level test) | (none) | shell/e2e/ (extend) | (meta) | new-only | XS | 0.25 | P1 | P2a | todo |  | WI-20 | Test fails if any file in shell/src/plugins/{nexus,community}/ imports from '@tauri-apps/api' or the shell's host internals directly. Only @nexus/extension-api imports are permitted. | Enforces 'shell plugins are JS clients' invariant from shell-kernel-bridge-plan.md.

## Rollup
Metric | Value
Total work items | 23
P0 items | 5
P1 items | 7
P2 items | 8
P3 items | 3
Total estimated weeks | 19.25
P0 weeks (blockers) | 5.75
P1 weeks | 5.25
P2 weeks | 6
P3 weeks | 2.25
P2a weeks | 9.5
P2b weeks | 5
P2c weeks | 4.75
Completion % | 0%

## Legend
Column | Meaning
ID | Stable work-item identifier (WI-NN). Use in commit messages and PR titles.
Title | Short action-oriented title.
Service crate | Which crates/nexus-* crate owns the backing IPC handler (or 'shell-local' / 'none').
Kernel IPC | Exact IPC command(s) the shell plugin calls via api.kernel.invoke().
Shell plugin | Target plugin path in shell/src/ (existing or new).
Legacy handler(s) | #[tauri::command] fns in crates/nexus-app to retire when this item ships.
Gap | only-app = port needed. partial = finish weaker side. architectural-diff = decision required. new-only = no legacy equivalent (validation or guardrail work).
Size | XS ≤ 1 day · S ≈ 3 days · M ≈ 1 week · L ≈ 2 weeks · XL ≈ 3 weeks. Single-engineer estimates.
Est wk | Auto: size → weeks. Override manually if needed.
Priority | P0 ships-blocker · P1 high · P2 normal · P3 nice-to-have.
Phase | P2a first wave (leverage) · P2b features · P2c polish/decisions.
Status | todo · in-progress · done · blocked.
Owner | Assignee. Blank = unclaimed.
Dependencies | WI-IDs that must ship first.
Acceptance | Binary 'done when …' test for the work item.
Notes | Anything that doesn't fit elsewhere.
Phase ordering
P2a | Leverage items (AI, theme, editor, files, API wiring, guardrails). Ships first; unblocks downstream.
P2b | Feature completeness (agent, skills, workflow, bases, canvas, streaming). Depends on P2a foundations.
P2c | Peripheral + decisions (URI, persistence migration, layout-preset/menu-bar/ribbon ADR-level calls). Can slip without blocking v1 if scoped tight.